## Slide 2
Could Co-Sourcing Some Audits be the Answer?
Enhancing Audit Efficiency Through Strategic Partnerships
Mary M. Barnett
Chief Audit Executive
Virginia Community College System
March 11, 2025

## Slide 3
Background & Initial Challenges
Original team: Four auditors, an admin assistant, and CAE
Attempted to replace our IT auditor but faced budget limitations
Pivoted to co-sourcing IT audits instead
Lesson #1: Should have allocated full budget, including benefits, to co-sourcing

## Slide 4
The Move Toward More Co-Sourcing
Two resignations, one retirement, one unfilled new position
Four failed searches
Audit Committee stepped in: Need to get some audits done

## Slide 5
Arguments in Favor
Co-sourcing allows for flexible resource scaling
Eliminates time investment in one-time specialized areas
Can utilize subject-matter experts instead

## Slide 6
Selecting the Right Firm
First Step: IT Auditor
Key criteria:
  Strong recommendations
  Higher education experience
  Flexible contracts to bypass lengthy RFP processes
IT auditor provided valuable expertise during negotiations

## Slide 7
IT Audit Co-Sourcing Model
Initially assigned specific audits but moved to a retainer model
13 hours/week with a fixed monthly payment
Gary feels like a partner
Lesson #2: Work with someone you are comfortable with

## Slide 8
General Audit Co-Sourcing Model
Focused on firms with broad expertise
Pay only for work performed (prevents charges while waiting on data)
  Aligns with internal auditors working on multiple projects simultaneously

## Slide 9
Lessons Learned – Underestimating Bandwidth
Assumed I could manage contracts & audits while fulfilling CAE duties
George Mason model: CAE, Assistant Director, and IT Auditor roles
Lesson #3: Cannot outsource the work of an Assistant Director

## Slide 10
Lessons Learned - Managing Contracted Workload
Planned based on funds, but underestimated personal capacity
Struggled with reallocating resources when audits were canceled
Lesson #4: Need a plan for reassigning resources efficiently

## Slide 11
Lessons Learned - Contract Management
Not initially experienced in contract setup & invoice approvals
Early struggles with procurement & payment processes
Lesson #5: Clarify administrative requirements in advance

## Slide 12
Audit Selection Strategy
Prioritizing audits with the highest return on investment
Avoiding areas already covered by external audits
Early co-sourced audits required high involvement by CAE but will improve over time

## Slide 13
Northern Virginia Community College
NOVA proposed funding an internal auditor (failed searches)
Alternative: Use co-sourced auditors for targeted audits, paid by NOVA
Potential Model: Colleges fund specific audits without hiring permanent staff

## Slide 14
Implementation & Supervision
Launched three audits:
  HR Orientation
  Funding Model
  Student Travel (later replaced by Dual Enrollment)
Required separate contracts, invoices, and procurement navigation

## Slide 15
Unique Challenges in a Community College System
23 colleges = 23 CFOs, 23 CAOs, and multiple business officers
Each audit involves new stakeholders, increasing complexity
Continued involvement from CAE/Assistant Director likely necessary in many cases

## Slide 16
Conclusion
Co-sourcing ensures audits get done despite staffing challenges
Higher per-hour cost but only pay for necessary work
Contract oversight delegation is key to long-term sustainability
Final Lesson: A structured, strategic approach makes co-sourcing a success

## Slide 17
Thank you